## Summary Dashboard
HR & Payroll UAT Summary Dashboard
Formula-driven status. Refreshes automatically when execution and route results are updated.
Deep Tests | 41 |  | Route Coverage | 250
Result | Deep Tests | Route Coverage | Total
Pass
Fail
Blocked
Not Run
N/A
Open Critical / High Defects
Production Decision

## Test Execution
HR & Payroll Manual Test Execution
Deep end-to-end scenarios. Record actual outcomes and attach evidence before assigning Pass.
Test ID | Phase | Domain | Test Case | Routes | Preconditions | Role / Tester | Test Data | Test Steps | Expected Outcome | Actual Outcome | Result | Severity | Defect ID | Evidence | Tested By | Test Date | Retest Result | Retest Date | Comments | Build / Version | Environment
E2E-001 | 6. Phase A: Platform, Routing, and Access | Platform, Routing, and Access | Canonical route hard refresh | All routes listed in Section 21 | See Sections 4-5 and preceding workflow state. | HR-PREP | Use unique <RUN> data from Section 5. | 1. Open each critical route directly in a new browser tab. 2. Hard refresh the page. 3. Test at least employees, recruitment vacancies, leave applications, attendance imports, payroll input, payroll runs, approvals dashboard, analytics workforce, privacy audit, and accounting chart of accounts. | Every authorized route renders its normal layout without a blank page, 404, console crash, or stale mock records. Unauthorized routes show a controlled access-denied state. |  | Not Run |  |  | Route list, screenshots, browser console, and network status.
E2E-002 | 6. Phase A: Platform, Routing, and Access | Platform, Routing, and Access | Read-only permission enforcement | All create, edit, approve, post, publish, export, and delete actions under /hr/* and /accounting/coa | See Sections 4-5 and preceding workflow state. | RESTRICTED | Use unique <RUN> data from Section 5. | Open create/edit actions for employees, offers, attendance, payroll inputs, payroll runs, and approvals; attempt the corresponding API requests if the button is hidden. | The UI does not offer unauthorized actions and the backend returns a controlled 403 response without mutation. No raw exception or blank page appears. |  | Not Run |  |  | Response, unchanged record, and security/audit log where applicable.
E2E-003 | 6. Phase A: Platform, Routing, and Access | Platform, Routing, and Access | Tenant isolation | All record detail, API-backed table, drawer, export, and download routes under /hr/* | See Sections 4-5 and preceding workflow state. | TENANT-B-ADMIN | Use unique <RUN> data from Section 5. | Attempt to list, open, update, approve, export, or download Tenant A records using copied Tenant A IDs and references. | Tenant A data is never returned. Requests produce not-found or access-denied responses and no Tenant A record changes. |  | Not Run |  |  | Requests/responses, database verification, and audit/security log.
E2E-004 | 6. Phase A: Platform, Routing, and Access | Platform, Routing, and Access | User management and segregation of duties | /users -> /users/add -> /users/roles -> /users/status -> /users/security -> /users/passwords -> /users/logs -> /approvals/users | See Sections 4-5 and preceding workflow state. | Tenant administrator and user approver | Use unique <RUN> data from Section 5. | 1. Create the test users in Section 4 with unique email addresses. 2. Assign the minimum role and permissions required for each responsibility. 3. Submit users/roles for approval where configured. 4. Activate approved users and verify login. 5. Attempt to assign payroll preparation, payroll approval, and payment authorization to the same restricted test user. 6. Suspend one user, reset another user's password, revoke a role, and review login/security logs. | User creation, approval, role assignment, activation, suspension, password reset, and revocation are permissioned and audited. Suspended users cannot authenticate; revoked permissions take effect promptly. The configured segregation policy prevents or flags incompatible payroll roles. No user can access another tenant. |  | Not Run |  |  | User records, approval decision, role matrix, denied login/action, and security logs.
E2E-010 | 7. Phase B: Organization and Employee Foundation | Organization and Employee Foundation | Create department, position, cost centre, and salary structure | /hr/departments -> /hr/positions -> /accounting/coa -> /hr/payroll/cost-centres -> /hr/payroll/structures -> /hr/payroll/structure-components | See Sections 4-5 and preceding workflow state. | HR-PREP, PAY-PREP | Use unique <RUN> data from Section 5. | 1. Create the E2E department and position. 2. Create the cost centre with a valid GL account and live department. 3. Create a salary structure using a live pay band and verify minimum, maximum, and currency. 4. Assign valid payroll components. | Each record receives a human-readable unique reference, appears once in its table, and displays names instead of database IDs. Relationships persist after refresh. |  | Not Run |  |  | Detail screens and persisted records.
E2E-011 | 7. Phase B: Organization and Employee Foundation | Organization and Employee Foundation | Create current employees | /hr/employees -> /hr/employees/profiles -> /hr/history | See Sections 4-5 and preceding workflow state. | HR-PREP | Use unique <RUN> data from Section 5. | Create the current employee and separation-test employee with department, position, manager, hire date, employment status, currency, salary structure, and required statutory/payment fields. | Both appear as current employees in eligible selectors, directory, current headcount, and employee mappings. Employee numbers are unique and human readable. |  | Not Run |  |  | Employee profiles, directory, selector screenshots, and headcount value.
E2E-020 | 8. Phase C: Recruit-to-Hire | Recruit-to-Hire | Vacancy approval gate | /hr/recruitment/jobs -> /hr/recruitment/vacancies/eligibility -> /hr/recruitment/vacancies/forms -> /hr/recruitment/vacancies/approvals -> /hr/recruitment/vacancies/portal -> /hr/approvals/recruitment | See Sections 4-5 and preceding workflow state. | HR-PREP, HR-APPROVER | Use unique <RUN> data from Section 5. | 1. Create a vacancy linked to the E2E department and position. 2. Attempt to publish or fill it before approval. 3. Submit it for approval. 4. Reject it with a reason, revise, resubmit, and approve it. | An unapproved vacancy cannot publish or be filled. Rejection requires a reason and preserves history. Approval records approver and time; only the approved version can publish. |  | Not Run |  |  | Vacancy states, approval history, and denied action response.
E2E-021 | 8. Phase C: Recruit-to-Hire | Recruit-to-Hire | Candidate intake, consent, and duplicate protection | /hr/recruitment/candidates -> /hr/recruitment/candidates/database -> /hr/recruitment/candidates/profiles -> /hr/recruitment/candidates/consent -> /hr/recruitment/candidates/duplicates -> /hr/recruitment/candidates/communications | See Sections 4-5 and preceding workflow state. | HR-PREP | Use unique <RUN> data from Section 5. | Create the candidate, record consent, link the candidate to the vacancy, then attempt to create a duplicate using the same identifying data. | The candidate is linked once. The duplicate is detected or routed through the duplicate-review process; no silent duplicate profile is created. Consent is visible only to authorized users. |  | Not Run |  |  | Candidate record, duplicate case, and consent evidence.
E2E-022 | 8. Phase C: Recruit-to-Hire | Recruit-to-Hire | Interview and decision evidence | /hr/recruitment/pipeline -> /hr/recruitment/interviews -> /hr/recruitment/interviews/panels -> /hr/recruitment/interviews/assignments -> /hr/recruitment/interviews/conflicts -> /hr/recruitment/interviews/scorecards -> /hr/recruitment/interviews/evaluations -> /hr/recruitment/interviews/ranking | See Sections 4-5 and preceding workflow state. | HR-PREP, MANAGER-A | Use unique <RUN> data from Section 5. | Schedule an interview, assign the panel, record conflict declarations, submit scorecards/evaluations, and select the preferred candidate. | Selection cannot complete while required scorecards or conflict declarations are missing. Completed evidence is linked to the candidate and vacancy. AI ranking remains advisory and does not approve the candidate. |  | Not Run |  |  | Interview, scorecards, conflict records, and decision history.
E2E-023 | 8. Phase C: Recruit-to-Hire | Recruit-to-Hire | Medical and offer approval gates | /hr/recruitment/offers/background -> /hr/recruitment/offers/references -> /hr/recruitment/offers/medical -> /hr/recruitment/offers/medical-clearance -> /hr/approvals/medical -> /hr/recruitment/offers -> /hr/approvals/offers -> /hr/recruitment/offers/signatures -> /hr/recruitment/offers/acceptance | See Sections 4-5 and preceding workflow state. | HR-PREP, HR-APPROVER | Use unique <RUN> data from Section 5. | 1. Create required checks and medical assessment. 2. Attempt to advance with an unapproved medical assessment. 3. Approve the medical assessment. 4. Create an offer and attempt send/accept/convert before offer approval. 5. Approve, send, and accept the offer. | Required medical and offer approvals are backend enforced. Premature actions fail with human-readable in-context messages. Approved actions retain actor, date, and evidence. |  | Not Run |  |  | States, denied responses, approval records, and audit events.
E2E-024 | 8. Phase C: Recruit-to-Hire | Recruit-to-Hire | Candidate conversion is idempotent | /hr/recruitment/offers/acceptance -> /hr/approvals/appointment-letters -> /hr/onboarding/pre -> /hr/onboarding/new | See Sections 4-5 and preceding workflow state. | HR-PREP | Use unique <RUN> data from Section 5. | Convert the accepted offer to onboarding/employee, then repeat the conversion action. | Exactly one employee and one onboarding handoff are created. The repeat action returns a controlled “already converted” outcome and creates no duplicates. |  | Not Run |  |  | Employee/candidate linkage, onboarding case, record counts, and audit event.
E2E-030 | 9. Phase D: Onboarding and Probation | Onboarding and Probation | Mandatory onboarding gate | /hr/onboarding/pre -> /hr/onboarding/new -> /hr/onboarding/checklists -> /hr/onboarding/documents -> /hr/onboarding/assets -> /hr/onboarding/it-provisioning -> /hr/onboarding/orientation -> /hr/onboarding/completion | See Sections 4-5 and preceding workflow state. | HR-PREP, MANAGER-A | Use unique <RUN> data from Section 5. | Assign checklist, documents, provisioning, assets, orientation, and required training. Attempt completion with one mandatory item open; then complete it and close onboarding. | Completion is blocked while mandatory work is open and names the blocker. After completion, onboarding closes once and retains all evidence. |  | Not Run |  |  | Checklist before/after, denied response, closure event.
E2E-031 | 9. Phase D: Onboarding and Probation | Onboarding and Probation | Probation decision | /hr/onboarding/probation-settings -> /hr/onboarding/probation -> /hr/settings/probation -> /hr/history | See Sections 4-5 and preceding workflow state. | MANAGER-A, HR-APPROVER | Use unique <RUN> data from Section 5. | Record a probation review, submit confirmation/extension decision, approve it, and verify the employee state. | The decision follows configured approval and effective-date rules. Employee master data changes only after the approved action is applied. |  | Not Run |  |  | Review, decision, approval, employee history, and audit record.
E2E-040 | 10. Phase E: Attendance | Attendance | Attendance directory mapping | /hr/attendance/devices -> /hr/attendance/devices/sources -> /hr/attendance/directory -> /hr/attendance/directory/add -> /hr/attendance/directory/profiles -> /hr/attendance/directory/status | See Sections 4-5 and preceding workflow state. | HR-PREP | Use unique <RUN> data from Section 5. | Map the current employee to an attendance device/source with unique biometric and external IDs; attempt duplicate IDs and duplicate employee mapping. | Valid mapping saves once. Duplicates produce specific human-readable errors. Separated or already-mapped employees are not offered as new mappings. |  | Not Run |  |  | Mapping, selector, and duplicate error.
E2E-041 | 10. Phase E: Attendance | Attendance | Template-based attendance import | /hr/attendance/devices/templates -> /hr/attendance/settings/import -> /hr/attendance/settings/parsing -> /hr/attendance/settings/timezone -> /hr/attendance/settings/duplicates -> /hr/attendance/imports -> /hr/attendance/imports/validation -> /hr/attendance/imports/failed -> /hr/attendance/imports/history -> /hr/attendance/logs | See Sections 4-5 and preceding workflow state. | HR-PREP | Use unique <RUN> data from Section 5. | 1. Create a CSV/Excel template using human-readable column mappings. 2. Upload a file containing valid rows, a duplicate, an unknown employee, and an invalid timestamp. 3. Preview and validate without posting. 4. Correct/match failed rows and post the batch. | Preview does not create logs. Validation identifies each issue and preserves the source row. Final posting creates valid logs once, excludes unresolved rows, and records batch/row lineage. |  | Not Run |  |  | Template, preview, failures, posted logs, and duplicate counts.
E2E-042 | 10. Phase E: Attendance | Attendance | Automated attendance synchronization | /hr/attendance/imports/sync -> /hr/attendance/analytics/sync -> /hr/attendance/imports/history -> /hr/attendance/reports/imports | See Sections 4-5 and preceding workflow state. | HR-PREP | Use unique <RUN> data from Section 5. | Configure an active connector and schedule, queue a sync, attempt to queue a second overlapping job, and run the worker. | One job processes through queued/running/completed or failed states. Overlap is prevented. Credentials are not displayed or exported. Counts and error logs reconcile to imported rows. |  | Not Run |  |  | Source, job history, worker log, and resulting batch/logs.
E2E-043 | 10. Phase E: Attendance | Attendance | Attendance exception and payroll readiness | /hr/attendance/monitoring/live -> /hr/attendance/monitoring/clock-in -> /hr/attendance/monitoring/clock-out -> /hr/attendance/monitoring/shift -> /hr/attendance/exceptions -> /hr/attendance/adjustments -> /hr/attendance/review/queue -> /hr/attendance/review/approvals -> /hr/attendance/review/payroll -> /hr/payroll/runs | See Sections 4-5 and preceding workflow state. | HR-PREP, HR-APPROVER | Use unique <RUN> data from Section 5. | Create an attendance exception for the current employee, verify the employee name displays, and attempt payroll generation before and after correction/approval. | The open material exception blocks payroll generation with a message in the payroll drawer. Correcting/approving it removes the blocker without deleting its history. |  | Not Run |  |  | Exception states, payroll responses, and audit trail.
E2E-050 | 11. Phase F: Leave | Leave | Working-day calculation | /hr/leave/types -> /hr/leave/applications -> /hr/self-service/leave | See Sections 4-5 and preceding workflow state. | EMPLOYEE-A | Use unique <RUN> data from Section 5. | Create leave applications spanning weekdays only, one weekend, and two weekends. | Total days include the start/end dates where applicable and exclude Saturdays and Sundays. Invalid date order is rejected. |  | Not Run |  |  | Input dates and calculated totals.
E2E-051 | 11. Phase F: Leave | Leave | Leave approval and balance | /hr/leave/applications -> /hr/leave/approvals -> /hr/leave/balances -> /hr/leave/calendar | See Sections 4-5 and preceding workflow state. | EMPLOYEE-A, MANAGER-A | Use unique <RUN> data from Section 5. | Submit leave, reject with reason, resubmit, approve, and inspect balance/calendar. | Pending leave affects pending balance only. Approved leave updates used/available balance and calendar once. Rejection reason and complete approval history remain visible. |  | Not Run |  |  | Request states, balances before/after, calendar, and audit.
E2E-060 | 12. Phase G: Performance, Training, and Employee Relations | Performance, Training, and Employee Relations | Performance review lifecycle | /hr/performance/cycles -> /hr/performance/scorecards -> /hr/performance/scorecard-categories -> /hr/performance/appraisals -> /hr/performance/kpis -> /hr/performance/reviews -> /hr/performance/review-categories -> /hr/performance/feedback -> /hr/performance/calibration -> /hr/performance/talent-reviews -> /hr/performance/succession -> /hr/performance/ai | See Sections 4-5 and preceding workflow state. | HR-PREP, MANAGER-A | Use unique <RUN> data from Section 5. | Create a cycle, appraisal, employee KPI, review, feedback, and calibration record. Complete required stages and finalize. | Current employee lists exclude separated employees. Review references are generated, employee names display, scores follow configured rules, and finalization is blocked until required evidence is complete. |  | Not Run |  |  | Cycle, KPI, review states, calibration, and audit.
E2E-061 | 12. Phase G: Performance, Training, and Employee Relations | Performance, Training, and Employee Relations | Employee relations linkage | /hr/employee-relations/grievances -> /hr/employee-relations/investigations -> /hr/lifecycle/disciplinary -> /hr/employee-relations/actions | See Sections 4-5 and preceding workflow state. | HR-PREP, HR-APPROVER | Use unique <RUN> data from Section 5. | Create a grievance, investigation, disciplinary case, and action for the current employee. Change the selected employee during creation. | Assigned-to/investigator selectors use current employees. Linked grievance, investigation, and disciplinary choices belong only to the selected employee. Approval actions retain evidence. |  | Not Run |  |  | Selector screenshots, saved relationships, and audit.
E2E-070 | 13. Phase H: Payroll Configuration and Input | Payroll Configuration and Input | Payroll configuration validation | /hr/payroll/currencies -> /hr/payroll/exchange-rates -> /hr/payroll/components -> /hr/payroll/structures -> /hr/payroll/structure-components -> /hr/payroll/employee-components -> /hr/payroll/statutory-rules -> /hr/payroll/cost-centres -> /accounting/coa | See Sections 4-5 and preceding workflow state. | PAY-PREP, FINANCE | Use unique <RUN> data from Section 5. | Verify currencies, exchange rate, PAYE/statutory rules, structures, components, cost centre GL account, and payroll accounting accounts for the test period. | Only effective active configuration is used. Duplicate exchange rates return a human-readable error. Missing required accounting/statutory configuration is named before posting/generation. |  | Not Run |  |  | Configuration records and validation messages.
E2E-071 | 13. Phase H: Payroll Configuration and Input | Payroll Configuration and Input | Payroll input create/update/validate | /hr/payroll/input -> /hr/payroll/change-requests -> /hr/payroll/bonuses -> /hr/payroll/backpay -> /hr/payroll/deductions -> /hr/payroll/loans -> /hr/benefits -> /hr/benefits/enrollments -> /hr/payroll/validation -> /hr/payroll/exceptions | See Sections 4-5 and preceding workflow state. | PAY-PREP | Use unique <RUN> data from Section 5. | Add payroll input for the current employee with cost centre and components; save changes; edit the same employee/period; use Save & Validate. | The existing employee/period input updates rather than duplicating. Saved values remain after refresh. Save & Validate checks required fields/business rules and changes status to validated only when all checks pass. |  | Not Run |  |  | Before/after drawer, row count, persisted values, status, and validation details.
E2E-072 | 13. Phase H: Payroll Configuration and Input | Payroll Configuration and Input | Cost-centre consistency | /hr/payroll/input <-> /hr/payroll/cost-centres | See Sections 4-5 and preceding workflow state. | PAY-PREP | Use unique <RUN> data from Section 5. | Assign/remap the current employee's cost centre from payroll input and cost-centre mapping views. | Both views resolve the same live cost centre, mapped headcount, allocation, and monthly cost after refresh. There is one authoritative mapping. |  | Not Run |  |  | Both pages and persisted payroll-input metadata.
E2E-080 | 14. Phase I: Payroll Run to Accounting and Payslip | Payroll Run to Accounting and Payslip | Create and generate payroll run | /hr/payroll/runs -> /hr/attendance/review/payroll -> /hr/payroll/validation -> /hr/payroll/exceptions | See Sections 4-5 and preceding workflow state. | PAY-PREP | Use unique <RUN> data from Section 5. | Create the test-period run and generate items. | The run is created once, remains visible after refresh, and opens a stable detail drawer. Generation includes each eligible current employee once, excludes separated employees, calculates gross/deductions/tax/statutory/net, and links approved attendance/leave evidence. |  | Not Run |  |  | Run, employee items, calculation snapshots, record counts, and totals.
E2E-081 | 14. Phase I: Payroll Run to Accounting and Payslip | Payroll Run to Accounting and Payslip | Payroll reconciliation | /hr/payroll/runs -> /hr/payroll-governance/variance -> /hr/reports/register -> /hr/reports/exceptions -> /hr/reports/tax -> /hr/reports/contributions | See Sections 4-5 and preceding workflow state. | PAY-PREP, PAY-APPROVER | Use unique <RUN> data from Section 5. | Reconcile generated items to current employees, approved changes, components, cost centres, attendance/leave, statutory records, and prior period. | Sum of item gross, deductions, and net equals run totals. Currency totals are not combined without conversion. Variances and exceptions are explainable and resolved or approved. |  | Not Run |  |  | Signed reconciliation worksheet and system reports.
E2E-082 | 14. Phase I: Payroll Run to Accounting and Payslip | Payroll Run to Accounting and Payslip | Payroll approval segregation | /hr/approvals/payroll -> /hr/payroll-governance/approvals -> /hr/payroll-governance/workflow -> /hr/payroll-governance/audit -> /hr/approvals/audit | See Sections 4-5 and preceding workflow state. | PAY-PREP, PAY-APPROVER | Use unique <RUN> data from Section 5. | Submit the run; attempt self-approval as PAY-PREP; approve as PAY-APPROVER; repeat approval. | Self-approval is denied where segregation is configured. Independent approval succeeds once. Repeat approval is idempotent. Actor, time, note, and run version are recorded. |  | Not Run |  |  | Responses and approval audit.
E2E-083 | 14. Phase I: Payroll Run to Accounting and Payslip | Payroll Run to Accounting and Payslip | Post payroll accrual to accounting | /hr/payroll/runs -> /accounting/journals -> /accounting/ledger -> /accounting/trial-balance | See Sections 4-5 and preceding workflow state. | PAY-APPROVER, FINANCE | Use unique <RUN> data from Section 5. | Post the approved run to accounting, inspect the journal, and repeat the post action. | One balanced accrual journal is created with payroll run reference and configured accounts. Debits equal credits. Repeat posting creates no duplicate journal. Missing/invalid accounts block posting and name the configuration issue. |  | Not Run |  |  | Journal header/lines, balance, payroll link, and repeat response.
E2E-084 | 14. Phase I: Payroll Run to Accounting and Payslip | Payroll Run to Accounting and Payslip | Payment authorization and posting | /hr/approvals/salary-authorization -> /hr/payroll-governance/pending-salary -> /hr/payroll-governance/authorization -> /hr/payroll-governance/authorized-salary -> /accounting/journals | See Sections 4-5 and preceding workflow state. | PAY-AUTH, FINANCE | Use unique <RUN> data from Section 5. | Authorize salary payment, post payment, inspect payment journal, and repeat the action. | Authorization requires the independent role and approved/posted payroll state. One balanced payment journal settles the payroll payable account. Repeat posting is prevented. |  | Not Run |  |  | Authorization, payment journal, account balances, and audit.
E2E-085 | 14. Phase I: Payroll Run to Accounting and Payslip | Payroll Run to Accounting and Payslip | Payslip generation, publication, and privacy | /hr/payroll/runs -> /hr/payroll-governance/exports -> /hr/self-service/payslips | See Sections 4-5 and preceding workflow state. | PAY-PREP, EMPLOYEE-A | Use unique <RUN> data from Section 5. | Generate and publish payslips, open Employee A self-service payslip, attempt access to another employee's payslip, then unpublish where permitted. | Payslips match finalized items. Employee A can access only Employee A's published payslip. Cross-employee access is denied. Publish/unpublish actions are audited and do not change payroll values. |  | Not Run |  |  | Payslip, access responses, and audit.
E2E-090 | 15. Phase J: Separation and Current-Employee Enforcement | Separation and Current-Employee Enforcement | Approved separation | /hr/lifecycle/separation -> /hr/lifecycle/exit-interviews -> /hr/lifecycle/clearance -> /hr/payroll/runs -> /hr/history | See Sections 4-5 and preceding workflow state. | HR-PREP, HR-APPROVER | Use unique <RUN> data from Section 5. | Initiate resignation for the separation-test employee, approve it, complete exit interview/clearance/final-payroll stages as configured, and reach the effective separation state. | Separation records reason, dates, actor, approval, clearance, and final-payroll evidence. The employee's historical profile remains available to authorized users. |  | Not Run |  |  | Separation case, approval, related exit records, and employment history.
E2E-091 | 15. Phase J: Separation and Current-Employee Enforcement | Separation and Current-Employee Enforcement | Global separated-employee exclusion | Every create/edit employee selector under /hr/leave/*, /hr/attendance/*, /hr/performance/*, /hr/training/*, /hr/benefits/*, /hr/payroll/*, /hr/employee-relations/*, /hr/statutory/*, /hr/analytics/*, and /hr/ai/* | See Sections 4-5 and preceding workflow state. | HR-PREP, PAY-PREP | Use unique <RUN> data from Section 5. | Search for the separated employee in new leave, attendance mapping/log/exception, shift assignment, appraisal/KPI, benefit, payroll input, payroll exception, certificate, employee-relations assignee, and other current-employee selectors. | The separated employee appears in none of the new-transaction selectors and cannot be submitted by manually injecting the employee ID. The backend returns a human-readable validation response. |  | Not Run |  |  | Selector matrix and API responses.
E2E-092 | 15. Phase J: Separation and Current-Employee Enforcement | Separation and Current-Employee Enforcement | Historical visibility and analytics consistency | /hr/history -> /hr/analytics/workforce -> /hr/analytics/headcount -> /hr/analytics/attrition -> /hr/analytics/compensation -> /hr/ai/attrition-prediction -> /hr/reports/register | See Sections 4-5 and preceding workflow state. | HR-PREP, HR-APPROVER | Use unique <RUN> data from Section 5. | Inspect employee history, prior attendance, prior leave, prior performance, prior payroll, attrition analysis, headcount, compensation, reports, exports, and AI current-workforce pages. | Historical records retain the employee name/reference. Attrition history includes the exit appropriately. Current headcount, compensation, payroll readiness, current reports, and AI employee tables exclude the separated employee and reconcile to one current-employee population. |  | Not Run |  |  | Reconciliation sheet and screenshots.
E2E-100 | 16. Phase K: Reports, Analytics, AI, and Exports | Reports, Analytics, AI, and Exports | Report builder and saved/scheduled reports | /hr/analytics/report-builder -> /hr/analytics/saved -> /hr/analytics/scheduled -> /hr/analytics/exports | See Sections 4-5 and preceding workflow state. | HR-APPROVER | Use unique <RUN> data from Section 5. | Build a workforce report, preview, save, reopen, schedule, run, and export it. | Selected fields, filters, aggregation, grouping, and chart remain stable. Preview, saved report, scheduled result, and export reconcile. Current-workforce reports exclude separated employees. No mock rows appear when data is absent. |  | Not Run |  |  | Definition, preview, schedule run, export, and audit.
E2E-101 | 16. Phase K: Reports, Analytics, AI, and Exports | Reports, Analytics, AI, and Exports | Analytics drilldown reconciliation | All /hr/analytics/*, /hr/recruitment/analytics/*, /hr/attendance/analytics/*, /hr/attendance/intelligence/*, and /hr/training/analytics routes | See Sections 4-5 and preceding workflow state. | HR-APPROVER | Use unique <RUN> data from Section 5. | Compare workforce, headcount, compensation, recruitment, attendance, and approval KPIs to their table/drilldown records. | Every KPI defines its period/population and reconciles to its drilldown. Empty charts show an honest empty state. Currency and historical/current populations are clearly distinguished. |  | Not Run |  |  | KPI reconciliation worksheet.
E2E-102 | 16. Phase K: Reports, Analytics, AI, and Exports | Reports, Analytics, AI, and Exports | AI governance | /hr/ai/recruitment-assistant -> /hr/ai/candidate-matching -> /hr/ai/candidate-ranking -> /hr/ai/scoring-settings -> /hr/ai/interview-engine -> /hr/ai/attrition-prediction -> /hr/ai/workforce-planning -> /hr/ai/executive | See Sections 4-5 and preceding workflow state. | HR-APPROVER | Use unique <RUN> data from Section 5. | Review candidate matching/ranking, attrition prediction, workforce planning, and executive AI pages with and without configured model/scoring evidence. | AI is advisory, identifies evidence/gaps, does not fabricate probabilities or records, excludes terminal candidates from active queues, excludes separated employees from current-workforce tables, and performs no autonomous employment action. |  | Not Run |  |  | Screenshots, settings, source evidence, and audit where an action is taken.
E2E-110 | 17. Phase L: Privacy, Audit, Failure, and Recovery | Privacy, Audit, Failure, and Recovery | Employee data request | /hr/self-service/data-requests -> /hr/privacy/employee-data-requests -> /hr/privacy/audit | See Sections 4-5 and preceding workflow state. | PRIVACY | Use unique <RUN> data from Section 5. | Create a data access/correction request, verify identity, process it, and close it. | Due date, verification, owner, decision, response, and completion evidence are retained. Sensitive exports are protected and audited. |  | Not Run |  |  | Request lifecycle and export/access log.
E2E-111 | 17. Phase L: Privacy, Audit, Failure, and Recovery | Privacy, Audit, Failure, and Recovery | Deletion/RTBF with legal hold | /hr/privacy/consent -> /hr/privacy/retention -> /hr/privacy/deletion -> /hr/privacy/rtbf -> /hr/privacy/audit | See Sections 4-5 and preceding workflow state. | PRIVACY | Use unique <RUN> data from Section 5. | Create a deletion/RTBF request for a subject with payroll/statutory records and an active legal hold; attempt approval and execution. | The legal hold and statutory retention obligations prevent destructive deletion. The response explains the permitted action, and the decision is audited. |  | Not Run |  |  | Policy, hold, request decision, and privacy audit.
E2E-112 | 17. Phase L: Privacy, Audit, Failure, and Recovery | Privacy, Audit, Failure, and Recovery | Human-readable failure handling | Every modal, drawer, row action, import, export, approval, and posting surface under /hr/* | See Sections 4-5 and preceding workflow state. | Relevant preparer | Use unique <RUN> data from Section 5. | Trigger duplicate, required-field, invalid-date, invalid-state, missing-configuration, permission, and simulated server failures from drawers/modals. | Errors stay in context, preserve entries, provide actionable language, and do not expose SQLSTATE, constraints, stack traces, raw JSON, or secrets. The page does not turn blank. |  | Not Run |  |  | Error screenshots, network response, and secured server log correlation ID.
E2E-113 | 17. Phase L: Privacy, Audit, Failure, and Recovery | Privacy, Audit, Failure, and Recovery | Concurrency and repeat action | /hr/approvals/*, /hr/payroll/runs, /hr/payroll-governance/*, /hr/attendance/imports/*, /hr/recruitment/offers, and lifecycle action routes | See Sections 4-5 and preceding workflow state. | Two authorized users | Use unique <RUN> data from Section 5. | Submit simultaneous updates/approvals and double-click generate/post/publish actions. | Optimistic/state checks prevent lost updates. At most one terminal action succeeds; duplicates are not created; the other user receives a controlled stale/already-processed response. |  | Not Run |  |  | Requests, record counts, versions, and audit order.
E2E-114 | 17. Phase L: Privacy, Audit, Failure, and Recovery | Privacy, Audit, Failure, and Recovery | Backup and recovery exercise | All critical transaction routes plus restored database, file, worker, and accounting evidence | See Sections 4-5 and preceding workflow state. | Technical owner | Use unique <RUN> data from Section 5. | Back up the test database/files, execute representative transactions, restore to an isolated environment, and reconcile critical records. | Restore completes within the agreed objective. Employee, approvals, payroll items, journals, payslips, attendance lineage, files, and audits reconcile with the backup point. |  | Not Run |  |  | Backup/restore logs and signed reconciliation.

## Route Coverage
HR & Payroll Route Coverage
Every registered HR route plus user/access and accounting integration routes. Each row requires functional evidence.
Coverage ID | Domain | Route | Feature / Expected Outcome | Result | Actual Outcome | Severity | Defect ID | Evidence | Tested By | Test Date | Comments | Build / Version | Environment
ROUTE-001 | User management and access foundation | /users | Live tenant users, search, filters, details, and permitted row actions work. | Not Run
ROUTE-002 | User management and access foundation | /users/add | User creation validates identity, uniqueness, tenant, role, and approval requirements. | Not Run
ROUTE-003 | User management and access foundation | /users/roles | Role/permission assignments follow least privilege and segregation rules. | Not Run
ROUTE-004 | User management and access foundation | /users/status | Activate/suspend/reactivate actions require confirmation and are audited. | Not Run
ROUTE-005 | User management and access foundation | /users/security | MFA/session/security controls persist and unauthorized changes fail. | Not Run
ROUTE-006 | User management and access foundation | /users/passwords | Reset flow is secure, expiring, auditable, and does not expose credentials. | Not Run
ROUTE-007 | User management and access foundation | /users/logs | Authentication and security events are live, tenant scoped, and immutable. | Not Run
ROUTE-008 | User management and access foundation | /approvals/users | User/role approval decisions are independent, state controlled, and audited. | Not Run
ROUTE-009 | Foundation and employee master | /hr/departments | Create/edit live departments; references persist and inactive/deleted departments are unavailable to new transactions. | Not Run
ROUTE-010 | Foundation and employee master | /hr/positions | Create/edit positions linked to live departments, pay bands, and headcount; selectors show business names. | Not Run
ROUTE-011 | Foundation and employee master | /hr/employees | Current directory excludes separated employees; create/search/filter/actions use live data. | Not Run
ROUTE-012 | Foundation and employee master | /hr/employees/profiles | Profile drawer/page resolves employee, employment, organization, payroll, and history data without leaking sensitive fields. | Not Run
ROUTE-013 | Foundation and employee master | /hr/history | Historical lifecycle records retain employee names, references, effective dates, actors, and decisions. | Not Run
ROUTE-014 | Vacancies, candidates, interviews, and offers | /hr/recruitment/jobs | Vacancy CRUD uses live positions/departments and enforces approval before publication/fill. | Not Run
ROUTE-015 | Vacancies, candidates, interviews, and offers | /hr/recruitment/vacancies/eligibility | Rules save in human-readable form and are evaluated against the selected vacancy. | Not Run
ROUTE-016 | Vacancies, candidates, interviews, and offers | /hr/recruitment/vacancies/forms | Application form fields persist in order and are used by candidate intake. | Not Run
ROUTE-017 | Vacancies, candidates, interviews, and offers | /hr/recruitment/vacancies/approvals | Submit/approve/reject is permissioned, audited, and backend enforced. | Not Run
ROUTE-018 | Vacancies, candidates, interviews, and offers | /hr/recruitment/vacancies/portal | Only approved, active, in-date vacancies are published. | Not Run
ROUTE-019 | Vacancies, candidates, interviews, and offers | /hr/recruitment/vacancies/archived | Closed/expired/rejected vacancies remain read-only and traceable. | Not Run
ROUTE-020 | Vacancies, candidates, interviews, and offers | /hr/recruitment/candidates | Candidate list uses live records and valid stage actions. | Not Run
ROUTE-021 | Vacancies, candidates, interviews, and offers | /hr/recruitment/candidates/database | Search, filter, pagination, and detail drawers reconcile to candidate records. | Not Run
ROUTE-022 | Vacancies, candidates, interviews, and offers | /hr/recruitment/candidates/profiles | Profile evidence resolves documents, history, skills, and vacancy links. | Not Run
ROUTE-023 | Vacancies, candidates, interviews, and offers | /hr/recruitment/candidates/talent-pool | Eligible retained candidates can be added/removed with consent and audit evidence. | Not Run
ROUTE-024 | Vacancies, candidates, interviews, and offers | /hr/recruitment/candidates/communications | Communications link to the candidate and preserve delivery/status evidence. | Not Run
ROUTE-025 | Vacancies, candidates, interviews, and offers | /hr/recruitment/candidates/consent | Consent purpose, status, version, and timestamp are recorded and enforced. | Not Run
ROUTE-026 | Vacancies, candidates, interviews, and offers | /hr/recruitment/consent-management | Consent administration reconciles to candidate consent records. | Not Run
ROUTE-027 | Vacancies, candidates, interviews, and offers | /hr/recruitment/candidates/data-requests | Candidate privacy requests follow identity, due-date, decision, and closure controls. | Not Run
ROUTE-028 | Vacancies, candidates, interviews, and offers | /hr/recruitment/data-requests | Recruitment request queue contains no fabricated records and actions are audited. | Not Run
ROUTE-029 | Vacancies, candidates, interviews, and offers | /hr/recruitment/candidates/duplicates | Duplicate detection, merge/resolve, and repeat processing are idempotent. | Not Run
ROUTE-030 | Vacancies, candidates, interviews, and offers | /hr/recruitment/pipeline | Stage movement follows prerequisites and retains transition history. | Not Run
ROUTE-031 | Vacancies, candidates, interviews, and offers | /hr/recruitment/stage-exceptions | Stage bypass requires an approved exception and reason. | Not Run
ROUTE-032 | Vacancies, candidates, interviews, and offers | /hr/recruitment/interviews | Interview creation uses live candidates, vacancies, dates, and panel members. | Not Run
ROUTE-033 | Vacancies, candidates, interviews, and offers | /hr/recruitment/interviews/panels | Panel membership and roles persist and respect conflicts. | Not Run
ROUTE-034 | Vacancies, candidates, interviews, and offers | /hr/recruitment/interviews/assignments | Assignments are unique, visible to assignees, and status tracked. | Not Run
ROUTE-035 | Vacancies, candidates, interviews, and offers | /hr/recruitment/interviews/conflicts | Conflict declaration blocks participation until resolved/reassigned. | Not Run
ROUTE-036 | Vacancies, candidates, interviews, and offers | /hr/recruitment/interviews/scorecards | Approved criteria and scores persist; incomplete scorecards cannot finalize. | Not Run
ROUTE-037 | Vacancies, candidates, interviews, and offers | /hr/recruitment/interviews/evaluations | Evaluation totals and comments reconcile to scorecards. | Not Run
ROUTE-038 | Vacancies, candidates, interviews, and offers | /hr/recruitment/interviews/ranking | Ranking uses recorded evidence and remains advisory. | Not Run
ROUTE-039 | Vacancies, candidates, interviews, and offers | /hr/recruitment/interviews/analytics | Metrics reconcile to interviews and show honest empty states. | Not Run
ROUTE-040 | Vacancies, candidates, interviews, and offers | /hr/recruitment/offers/background | Background checks retain outcome, evidence, waiver, and actor. | Not Run
ROUTE-041 | Vacancies, candidates, interviews, and offers | /hr/recruitment/offers/references | Reference checks link to candidate and block where mandatory. | Not Run
ROUTE-042 | Vacancies, candidates, interviews, and offers | /hr/recruitment/offers/medical | Medical records are restricted and require approval where configured. | Not Run
ROUTE-043 | Vacancies, candidates, interviews, and offers | /hr/recruitment/offers/medical-clearance | Only approved clearance advances the candidate. | Not Run
ROUTE-044 | Vacancies, candidates, interviews, and offers | /hr/recruitment/offers | Offer values use selected candidate/vacancy and enforce approval before issue. | Not Run
ROUTE-045 | Vacancies, candidates, interviews, and offers | /hr/recruitment/offers/signatures | Signature status and signed evidence are immutable and access controlled. | Not Run
ROUTE-046 | Vacancies, candidates, interviews, and offers | /hr/recruitment/offers/acceptance | Accept/decline/expire/convert transitions are valid and idempotent. | Not Run
ROUTE-047 | Recruitment analytics and AI | /hr/recruitment/analytics/dashboard | KPIs reconcile to live vacancies/candidates/offers/hires. | Not Run
ROUTE-048 | Recruitment analytics and AI | /hr/recruitment/analytics/funnel | Funnel stages reconcile without double counting. | Not Run
ROUTE-049 | Recruitment analytics and AI | /hr/recruitment/analytics/sources | Source totals and conversions reconcile to candidates. | Not Run
ROUTE-050 | Recruitment analytics and AI | /hr/recruitment/analytics/time-to-hire | Date boundaries and completed-hire durations are accurate. | Not Run
ROUTE-051 | Recruitment analytics and AI | /hr/recruitment/analytics/time-to-fill | Approved vacancy-to-fill duration is accurate. | Not Run
ROUTE-052 | Recruitment analytics and AI | /hr/recruitment/analytics/offer-acceptance | Issued/accepted/declined/expired totals reconcile. | Not Run
ROUTE-053 | Recruitment analytics and AI | /hr/recruitment/analytics/diversity | Authorized aggregate data is privacy appropriate and not inferred. | Not Run
ROUTE-054 | Recruitment analytics and AI | /hr/recruitment/analytics/ai | AI insights use recorded recruitment evidence and disclose limitations. | Not Run
ROUTE-055 | Recruitment analytics and AI | /hr/ai/recruitment-assistant | Assistant summaries are live, advisory, and route to evidence. | Not Run
ROUTE-056 | Recruitment analytics and AI | /hr/ai/candidate-matching | Active candidates match approved vacancies; terminal candidates are excluded. | Not Run
ROUTE-057 | Recruitment analytics and AI | /hr/ai/candidate-ranking | Ranking explains factors/gaps and performs no autonomous decision. | Not Run
ROUTE-058 | Recruitment analytics and AI | /hr/ai/scoring-settings | Governed weights validate, version, and affect subsequent ranking. | Not Run
ROUTE-059 | Recruitment analytics and AI | /hr/settings/candidate-ai-scoring | Settings route is consistent with AI scoring administration. | Not Run
ROUTE-060 | Recruitment analytics and AI | /hr/ai/interview-engine | Recommendations require interview evidence and remain advisory. | Not Run
ROUTE-061 | Approvals and onboarding | /hr/approvals/dashboard | Canonical dashboard counts and links reconcile to domain queues. | Not Run
ROUTE-062 | Approvals and onboarding | /hr/approvals/recruitment | Recruitment decisions enforce permissions and vacancy gates. | Not Run
ROUTE-063 | Approvals and onboarding | /hr/approvals/offers | Approve/reject availability reflects state and required evidence. | Not Run
ROUTE-064 | Approvals and onboarding | /hr/approvals/medical | Medical approval is restricted and blocks unapproved advancement. | Not Run
ROUTE-065 | Approvals and onboarding | /hr/approvals/appointment-letters | Appointment letters cannot issue before required approval. | Not Run
ROUTE-066 | Approvals and onboarding | /hr/approvals/escalations | Overdue approvals escalate once to configured owners and remain traceable. | Not Run
ROUTE-067 | Approvals and onboarding | /hr/approvals/audit | Audit contains live immutable workflow decisions and export works. | Not Run
ROUTE-068 | Approvals and onboarding | /hr/onboarding/pre | Accepted candidates appear once with readiness evidence. | Not Run
ROUTE-069 | Approvals and onboarding | /hr/onboarding/new | Employee/onboarding creation is complete, linked, and idempotent. | Not Run
ROUTE-070 | Approvals and onboarding | /hr/onboarding/checklists | Templates/tasks persist and mandatory items block completion. | Not Run
ROUTE-071 | Approvals and onboarding | /hr/onboarding/documents | Upload/verify/reject/expiry controls work with secure file access. | Not Run
ROUTE-072 | Approvals and onboarding | /hr/onboarding/assets | Requests, allocation, return responsibility, and status are traceable. | Not Run
ROUTE-073 | Approvals and onboarding | /hr/onboarding/it-provisioning | Provisioning bundles, owners, SLA, and completion evidence persist. | Not Run
ROUTE-074 | Approvals and onboarding | /hr/onboarding/orientation | Sessions, attendees, dates, and completion are live and validated. | Not Run
ROUTE-075 | Approvals and onboarding | /hr/onboarding/probation-settings | Tenant probation defaults validate and affect new cases. | Not Run
ROUTE-076 | Approvals and onboarding | /hr/settings/probation | Settings alias is consistent and does not create duplicate configuration. | Not Run
ROUTE-077 | Approvals and onboarding | /hr/onboarding/probation | Confirm/extend/separate decisions follow approval and effective dates. | Not Run
ROUTE-078 | Approvals and onboarding | /hr/onboarding/completion | Blocking tasks/documents prevent closure; successful closure is idempotent. | Not Run
ROUTE-079 | Lifecycle, relations, training, and benefits | /hr/lifecycle/movements | Movement history uses names, dates, before/after values, and approvals. | Not Run
ROUTE-080 | Lifecycle, relations, training, and benefits | /hr/lifecycle/promotions | Employee selection populates old position/pay band/currency; approve then apply. | Not Run
ROUTE-081 | Lifecycle, relations, training, and benefits | /hr/lifecycle/transfers | Current values populate and approved transfer applies once. | Not Run
ROUTE-082 | Lifecycle, relations, training, and benefits | /hr/lifecycle/contract-renewals | Renewal dates/terms validate and update only after approval. | Not Run
ROUTE-083 | Lifecycle, relations, training, and benefits | /hr/lifecycle/contract-expirations | Expiry queue is date accurate and actions are traceable. | Not Run
ROUTE-084 | Lifecycle, relations, training, and benefits | /hr/lifecycle/retirement | Retirement plans use live employees and effective dates. | Not Run
ROUTE-085 | Lifecycle, relations, training, and benefits | /hr/lifecycle/separation | Separation uses current employees, valid reasons/dates, approval, and effective-state handling. | Not Run
ROUTE-086 | Lifecycle, relations, training, and benefits | /hr/lifecycle/exit-interviews | Exit interview links to the employee/case and retains responses, owner, and status. | Not Run
ROUTE-087 | Lifecycle, relations, training, and benefits | /hr/lifecycle/clearance | Asset/access/handover/final-payroll items block closure until complete or approved. | Not Run
ROUTE-088 | Lifecycle, relations, training, and benefits | /hr/lifecycle/disciplinary | Cases retain allegation, evidence, hearing, outcome, and approvals. | Not Run
ROUTE-089 | Lifecycle, relations, training, and benefits | /hr/employee-relations/grievances | Assignee is a current employee; create/detail/actions do not blank the page. | Not Run
ROUTE-090 | Lifecycle, relations, training, and benefits | /hr/employee-relations/investigations | Investigator is current; linked cases belong to selected employee. | Not Run
ROUTE-091 | Lifecycle, relations, training, and benefits | /hr/employee-relations/actions | Linked grievance/disciplinary/investigation records belong to selected employee. | Not Run
ROUTE-092 | Lifecycle, relations, training, and benefits | /hr/lifecycle/training | Lifecycle training view reconciles to canonical training records. | Not Run
ROUTE-093 | Lifecycle, relations, training, and benefits | /hr/training/programs | Program CRUD, status, dates, owner, and budget use live data. | Not Run
ROUTE-094 | Lifecycle, relations, training, and benefits | /hr/training/courses | Courses link to programs and persist requirements. | Not Run
ROUTE-095 | Lifecycle, relations, training, and benefits | /hr/training/sessions | Sessions validate dates, capacity, trainer, and course. | Not Run
ROUTE-096 | Lifecycle, relations, training, and benefits | /hr/training/enrollments | Current employees only; enroll/complete/cancel actions are audited. | Not Run
ROUTE-097 | Lifecycle, relations, training, and benefits | /hr/training/certifications | Issuance, expiry, employee, and course evidence persist. | Not Run
ROUTE-098 | Lifecycle, relations, training, and benefits | /hr/training/analytics | Completion/cost/certification metrics reconcile. | Not Run
ROUTE-099 | Lifecycle, relations, training, and benefits | /hr/benefits | Plans use live components, currency, provider, and effective status. | Not Run
ROUTE-100 | Lifecycle, relations, training, and benefits | /hr/benefits/enrollments | Current employees only; costs and effective dates flow to payroll as configured. | Not Run
ROUTE-101 | Leave and self-service | /hr/leave/types | Leave type CRUD validates entitlement, paid flag, and active status. | Not Run
ROUTE-102 | Leave and self-service | /hr/leave/applications | Current employee list, weekday calculation, balance validation, and submission work. | Not Run
ROUTE-103 | Leave and self-service | /hr/leave/approvals | Approve/reject is permissioned and updates balance/calendar once. | Not Run
ROUTE-104 | Leave and self-service | /hr/leave/balances | Entitlement, used, pending, carry-over, and available values reconcile. | Not Run
ROUTE-105 | Leave and self-service | /hr/leave/calendar | Approved live leave displays by employee/date without mock entries. | Not Run
ROUTE-106 | Leave and self-service | /hr/self-service | Employee dashboard shows only the authenticated employee's live data. | Not Run
ROUTE-107 | Leave and self-service | /hr/self-service/leave | Employee can submit/view own leave only. | Not Run
ROUTE-108 | Leave and self-service | /hr/self-service/payslips | Employee can view/download only own published payslips. | Not Run
ROUTE-109 | Leave and self-service | /hr/self-service/loans | Employee sees own loan applications/balances and valid actions. | Not Run
ROUTE-110 | Leave and self-service | /hr/self-service/documents | Employee sees permitted documents with secure downloads. | Not Run
ROUTE-111 | Leave and self-service | /hr/self-service/performance | Employee sees permitted review/KPI/feedback records only. | Not Run
ROUTE-112 | Leave and self-service | /hr/self-service/manager | Manager view contains only authorized direct reports and actions. | Not Run
ROUTE-113 | Leave and self-service | /hr/self-service/profile-change-requests | Changes require review and do not directly mutate protected master data. | Not Run
ROUTE-114 | Leave and self-service | /hr/self-service/data-requests | Employee can create and track own privacy request. | Not Run
ROUTE-115 | Performance and talent | /hr/performance/cycles | Cycle CRUD validates dates/status and supplies appraisal selectors. | Not Run
ROUTE-116 | Performance and talent | /hr/performance/scorecards | Templates persist categories/weights and apply to reviews. | Not Run
ROUTE-117 | Performance and talent | /hr/performance/scorecard-categories | Categories validate weights and ordering. | Not Run
ROUTE-118 | Performance and talent | /hr/performance/appraisals | Current employees only; review number, cycle, dates, and status persist. | Not Run
ROUTE-119 | Performance and talent | /hr/performance/kpis | Scope tabs enforce employee/team/department/position properties and relationships. | Not Run
ROUTE-120 | Performance and talent | /hr/performance/reviews | Review lifecycle, scores, comments, and actions are live and gated. | Not Run
ROUTE-121 | Performance and talent | /hr/performance/review-categories | Category scores reconcile to review total. | Not Run
ROUTE-122 | Performance and talent | /hr/performance/feedback | Feedback uses the intended Smart HR layout and preserves visibility rules. | Not Run
ROUTE-123 | Performance and talent | /hr/performance/calibration | Session details, participants, score changes, reasons, and approval persist. | Not Run
ROUTE-124 | Performance and talent | /hr/performance/compensation-recommendations | Recommendation links performance and compensation and follows approval. | Not Run
ROUTE-125 | Performance and talent | /hr/performance/succession | Critical positions use live positions; duplicates are prevented. | Not Run
ROUTE-126 | Performance and talent | /hr/performance/talent-reviews | Talent evidence is live, scoped, and auditable. | Not Run
ROUTE-127 | Performance and talent | /hr/performance/ai | AI insights use live governed evidence and remain advisory. | Not Run
ROUTE-128 | Attendance configuration, capture, and review | /hr/attendance/devices | Device CRUD, connectivity/status, source, and identifiers are live. | Not Run
ROUTE-129 | Attendance configuration, capture, and review | /hr/attendance/devices/sources | API/database/SFTP/service/manual sources validate configuration securely. | Not Run
ROUTE-130 | Attendance configuration, capture, and review | /hr/attendance/devices/templates | Human-readable column mapping and validation rules persist. | Not Run
ROUTE-131 | Attendance configuration, capture, and review | /hr/attendance/devices/mapping | Hidden legacy route does not appear in navigation and redirects/defers to directory mapping. | Not Run
ROUTE-132 | Attendance configuration, capture, and review | /hr/attendance/directory | Live mappings display current employees and unique identifiers. | Not Run
ROUTE-133 | Attendance configuration, capture, and review | /hr/attendance/directory/add | Current unmapped employees only; IDs validate and save once. | Not Run
ROUTE-134 | Attendance configuration, capture, and review | /hr/attendance/directory/profiles | Profile tabs use live attendance evidence; no false 100% with no records. | Not Run
ROUTE-135 | Attendance configuration, capture, and review | /hr/attendance/directory/status | Mapping/device status reflects live data and actions work. | Not Run
ROUTE-136 | Attendance configuration, capture, and review | /hr/attendance/settings/import | Import settings persist and affect subsequent batches. | Not Run
ROUTE-137 | Attendance configuration, capture, and review | /hr/attendance/settings/parsing | Date/time/column parsing rules validate and affect preview. | Not Run
ROUTE-138 | Attendance configuration, capture, and review | /hr/attendance/settings/timezone | Timezone conversion is correct at input, storage, and display. | Not Run
ROUTE-139 | Attendance configuration, capture, and review | /hr/attendance/settings/duplicates | Duplicate key/window policy is applied consistently. | Not Run
ROUTE-140 | Attendance configuration, capture, and review | /hr/attendance/settings/thresholds | Lateness/overtime/absence thresholds drive exceptions and analytics. | Not Run
ROUTE-141 | Attendance configuration, capture, and review | /hr/attendance/settings/notifications | Recipient/event settings save and generate traceable notifications. | Not Run
ROUTE-142 | Attendance configuration, capture, and review | /hr/attendance/imports | New batch accepts configured CSV/Excel and keeps errors in drawer. | Not Run
ROUTE-143 | Attendance configuration, capture, and review | /hr/attendance/imports/validation | Row validation, correction, matching, and posting controls work. | Not Run
ROUTE-144 | Attendance configuration, capture, and review | /hr/attendance/imports/failed | Failed rows expose reasons and permit authorized correction/revalidation. | Not Run
ROUTE-145 | Attendance configuration, capture, and review | /hr/attendance/imports/history | Batch counts/status/source/template/details reconcile. | Not Run
ROUTE-146 | Attendance configuration, capture, and review | /hr/attendance/imports/sync | Connector choice, schedule, queue, worker, retry, and overlap guard work. | Not Run
ROUTE-147 | Attendance configuration, capture, and review | /hr/attendance/logs | Date/time values save as valid timestamps; current employees only for new logs. | Not Run
ROUTE-148 | Attendance configuration, capture, and review | /hr/attendance/monitoring/live | Live presence contains backend records and refresh works. | Not Run
ROUTE-149 | Attendance configuration, capture, and review | /hr/attendance/monitoring/clock-in | Clock-in actions validate mapping, time, duplicate event, and state. | Not Run
ROUTE-150 | Attendance configuration, capture, and review | /hr/attendance/monitoring/clock-out | Clock-out requires open attendance and calculates worked time. | Not Run
ROUTE-151 | Attendance configuration, capture, and review | /hr/attendance/monitoring/shift | Live shift coverage and employee assignments reconcile. | Not Run
ROUTE-152 | Attendance configuration, capture, and review | /hr/attendance/monitoring/exceptions | Monitoring exception route reconciles to canonical exception records. | Not Run
ROUTE-153 | Attendance configuration, capture, and review | /hr/attendance/exceptions | Current employees only; names resolve; create/edit/resolve actions persist. | Not Run
ROUTE-154 | Attendance configuration, capture, and review | /hr/attendance/adjustments | Date fields are dates; adjustment approval and before/after evidence persist. | Not Run
ROUTE-155 | Attendance configuration, capture, and review | /hr/attendance/approvals | Attendance approval queue enforces independent decisions. | Not Run
ROUTE-156 | Attendance configuration, capture, and review | /hr/attendance/review/queue | Queue uses live records, pagination, valid actions, and detail drawers. | Not Run
ROUTE-157 | Attendance configuration, capture, and review | /hr/attendance/review-items | Route resolves and items reconcile to queue; no 404. | Not Run
ROUTE-158 | Attendance configuration, capture, and review | /hr/attendance/review/approvals | Approval decisions update queue state once. | Not Run
ROUTE-159 | Attendance configuration, capture, and review | /hr/attendance/review/disciplinary | Disciplinary referrals link employee, exception, and resulting case. | Not Run
ROUTE-160 | Attendance configuration, capture, and review | /hr/attendance/review/payroll | Row drawer shows linkage evidence; approved attendance links to eligible payroll run. | Not Run
ROUTE-161 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/shifts/definitions | Shift times, breaks, booleans, activation confirmations, and overnight rules persist. | Not Run
ROUTE-162 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/shifts/assignments | Current employees only; effective dates and overlaps validate. | Not Run
ROUTE-163 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/shifts/calendar | Calendar displays live assignments and date navigation works. | Not Run
ROUTE-164 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/shifts/rules | Rules persist and drive attendance calculations/exceptions. | Not Run
ROUTE-165 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/analytics/dashboard | KPI population and periods reconcile to logs and current employees. | Not Run
ROUTE-166 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/analytics/lateness | Trend/department/severity charts show live data or honest blank states. | Not Run
ROUTE-167 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/analytics/absenteeism | Absence metrics reconcile to schedules, approved leave, and logs. | Not Run
ROUTE-168 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/analytics/overtime | Overtime metrics reconcile to approved worked time. | Not Run
ROUTE-169 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/analytics/sync | Active attendance sources are selectable and queued jobs reconcile. | Not Run
ROUTE-170 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/analytics/performance | Performance metrics exclude deleted/separated current-workforce records as defined. | Not Run
ROUTE-171 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/intelligence/anomalies | Anomaly distribution/chart uses recorded evidence and drilldowns. | Not Run
ROUTE-172 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/intelligence/lateness | Intelligence explains evidence without fabricating risk. | Not Run
ROUTE-173 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/intelligence/risk | Risk indicators are governed, explainable, and advisory. | Not Run
ROUTE-174 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/intelligence/presence | Presence intelligence reconciles to live logs and shifts. | Not Run
ROUTE-175 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/reports/daily | Daily report filters, pagination, totals, drawer, and export reconcile. | Not Run
ROUTE-176 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/reports/monthly | Monthly employee/day totals reconcile to daily records. | Not Run
ROUTE-177 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/reports/shift | Shift report reconciles assignments, attendance, exceptions, and overtime. | Not Run
ROUTE-178 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/reports/imports | Import report reconciles batch totals, failures, duplicates, and postings. | Not Run
ROUTE-179 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/reports/exceptions | Exception report reconciles types, statuses, owners, and dates. | Not Run
ROUTE-180 | Shifts, attendance analytics, intelligence, and reports | /hr/attendance/reports/export | Export configuration and KPI/table values are live; generated file matches filters. | Not Run
ROUTE-181 | Payroll configuration and processing | /hr/payroll/currencies | Live currency CRUD, one base currency, activation, and display work. | Not Run
ROUTE-182 | Payroll configuration and processing | /hr/payroll/exchange-rates | Effective rates validate and duplicates produce human-readable errors. | Not Run
ROUTE-183 | Payroll configuration and processing | /hr/payroll/components | Component type/method/formula/tax/statutory settings persist and validate. | Not Run
ROUTE-184 | Payroll configuration and processing | /hr/payroll/structures | Live pay band populates min/max/currency; no mock options. | Not Run
ROUTE-185 | Payroll configuration and processing | /hr/payroll/structure-components | Component names resolve; assignment values/order and tips are correct. | Not Run
ROUTE-186 | Payroll configuration and processing | /hr/payroll/employee-components | Current employees only; effective components flow into generation. | Not Run
ROUTE-187 | Payroll configuration and processing | /hr/payroll/statutory-rules | Human-readable PAYE bands, effective dates, country, rates, and activation work. | Not Run
ROUTE-188 | Payroll configuration and processing | /hr/payroll/cost-centres | Live departments/GL accounts, edit/remap, mapping totals, and payroll input agree. | Not Run
ROUTE-189 | Payroll configuration and processing | /hr/payroll/input | Current employees only; unique employee/period update, cost centre, save, and validation work. | Not Run
ROUTE-190 | Payroll configuration and processing | /hr/payroll/change-requests | Request number, employee name, approval, before/after evidence, and apply behavior work. | Not Run
ROUTE-191 | Payroll configuration and processing | /hr/payroll/bonuses | Current employee selection, amount/currency/effective date, and approval work. | Not Run
ROUTE-192 | Payroll configuration and processing | /hr/payroll/backpay | Period/date basis, employee, amount, approval, and payroll inclusion reconcile. | Not Run
ROUTE-193 | Payroll configuration and processing | /hr/payroll/deductions | Rules, limits, dates, status, and payroll impact reconcile. | Not Run
ROUTE-194 | Payroll configuration and processing | /hr/payroll/loans | Application, approval, repayment, balance, and deductions reconcile. | Not Run
ROUTE-195 | Payroll configuration and processing | /hr/payroll/exceptions | Employee names resolve; current-employee edit rule and resolution work. | Not Run
ROUTE-196 | Payroll configuration and processing | /hr/payroll/validation | Issues are live, employee names resolve, actions update validation state. | Not Run
ROUTE-197 | Payroll configuration and processing | /hr/payroll/runs | Create/generate/approve/post/pay/payslip/publish/lock flow is gated and idempotent. | Not Run
ROUTE-198 | Payroll governance, statutory, and reports | /hr/payroll-governance/approvals | Live approval queue and decisions reconcile to payroll runs. | Not Run
ROUTE-199 | Payroll governance, statutory, and reports | /hr/payroll-governance/workflow | Configured stages/owners/SLAs enforce sequence. | Not Run
ROUTE-200 | Payroll governance, statutory, and reports | /hr/payroll-governance/authorization | Authorization uses approved runs and independent role. | Not Run
ROUTE-201 | Payroll governance, statutory, and reports | /hr/payroll-governance/pending-salary | Pending salary list reconciles to approved unpaid liabilities. | Not Run
ROUTE-202 | Payroll governance, statutory, and reports | /hr/payroll-governance/authorized-salary | Authorized records reconcile to payment state and evidence. | Not Run
ROUTE-203 | Payroll governance, statutory, and reports | /hr/payroll-governance/variance | Current/prior values and thresholds reconcile to run items. | Not Run
ROUTE-204 | Payroll governance, statutory, and reports | /hr/payroll-governance/locks | Lock/unlock permissions, confirmations, reason, and audit work. | Not Run
ROUTE-205 | Payroll governance, statutory, and reports | /hr/payroll-governance/overrides | Current employees only; field dropdown, tips, approval, and application work. | Not Run
ROUTE-206 | Payroll governance, statutory, and reports | /hr/payroll-governance/audit | Immutable events are live, paginated, filterable, and exportable. | Not Run
ROUTE-207 | Payroll governance, statutory, and reports | /hr/payroll-governance/exports | Files derive from approved scope, are secured, and audited. | Not Run
ROUTE-208 | Payroll governance, statutory, and reports | /hr/approvals/payroll | Canonical payroll approval gate blocks downstream actions until approved. | Not Run
ROUTE-209 | Payroll governance, statutory, and reports | /hr/approvals/salary-authorization | Individual salary authorization is live and independently controlled. | Not Run
ROUTE-210 | Payroll governance, statutory, and reports | /hr/statutory/tax | PAYE values derive from effective rules and payroll records. | Not Run
ROUTE-211 | Payroll governance, statutory, and reports | /hr/statutory/ssnit | SSNIT employee/employer contributions reconcile to payroll. | Not Run
ROUTE-212 | Payroll governance, statutory, and reports | /hr/statutory/pension | Pension tiers/contributions/status reconcile to payroll. | Not Run
ROUTE-213 | Payroll governance, statutory, and reports | /hr/statutory/deductions | Statutory deductions are live and linked to effective rules. | Not Run
ROUTE-214 | Payroll governance, statutory, and reports | /hr/statutory/certificates | Current employees only for new certificates; issuance/download is audited. | Not Run
ROUTE-215 | Payroll governance, statutory, and reports | /hr/statutory/regulatory | Obligations, periods, deadlines, statuses, and evidence are live. | Not Run
ROUTE-216 | Payroll governance, statutory, and reports | /hr/statutory/tax-filing | Checklist derives from filing/payroll evidence and contains no fake items. | Not Run
ROUTE-217 | Payroll governance, statutory, and reports | /hr/statutory/alerts | Alerts derive from real deadlines/issues and actions work. | Not Run
ROUTE-218 | Payroll governance, statutory, and reports | /hr/reports/register | Payroll register totals reconcile to finalized run items. | Not Run
ROUTE-219 | Payroll governance, statutory, and reports | /hr/reports/tax | Tax report reconciles to statutory records and payroll tax totals. | Not Run
ROUTE-220 | Payroll governance, statutory, and reports | /hr/reports/contributions | Contribution report reconciles employee/employer records. | Not Run
ROUTE-221 | Payroll governance, statutory, and reports | /hr/reports/exceptions | Exception report reconciles live issues and resolutions. | Not Run
ROUTE-222 | Payroll governance, statutory, and reports | /hr/reports/authorization | Authorization report reconciles actors, decisions, amounts, and dates. | Not Run
ROUTE-223 | Payroll governance, statutory, and reports | /hr/reports/approval-audit | Live events load, paginate 10 per page, filter, detail, and export. | Not Run
ROUTE-224 | Payroll governance, statutory, and reports | /hr/reports/compliance | Compliance controls derive from live statutory/payroll evidence. | Not Run
ROUTE-225 | Workforce analytics, reports, and AI | /hr/analytics/workforce | Live current-workforce metrics exclude separated employees. | Not Run
ROUTE-226 | Workforce analytics, reports, and AI | /hr/analytics/headcount | Headcount and dimensions reconcile to canonical current employees. | Not Run
ROUTE-227 | Workforce analytics, reports, and AI | /hr/analytics/attrition | Approved historical exits, reasons, periods, and rates reconcile. | Not Run
ROUTE-228 | Workforce analytics, reports, and AI | /hr/analytics/compensation | Eligible headcount, bands, equity, costs, and currencies reconcile. | Not Run
ROUTE-229 | Workforce analytics, reports, and AI | /hr/analytics/recruitment | Recruitment analytics reconcile to canonical recruitment records. | Not Run
ROUTE-230 | Workforce analytics, reports, and AI | /hr/analytics/report-builder | Two-column builder, fields, controls, preview, save/share/schedule/export work. | Not Run
ROUTE-231 | Workforce analytics, reports, and AI | /hr/analytics/saved | Live definitions, compact detail drawer, actions, and access scope work. | Not Run
ROUTE-232 | Workforce analytics, reports, and AI | /hr/analytics/scheduled | Schedule CRUD, next/last run, retry, approval, and output work. | Not Run
ROUTE-233 | Workforce analytics, reports, and AI | /hr/analytics/exports | Live secure exports, status, expiry, download, and audit work. | Not Run
ROUTE-234 | Workforce analytics, reports, and AI | /hr/ai/attrition-prediction | Current employee evidence excludes separated staff; historical exits remain aggregate history. | Not Run
ROUTE-235 | Workforce analytics, reports, and AI | /hr/ai/workforce-planning | Plans use current headcount, live positions/vacancies, and explicit assumptions. | Not Run
ROUTE-236 | Workforce analytics, reports, and AI | /hr/ai/executive | Executive insights route to live evidence and disclose limitations. | Not Run
ROUTE-237 | Privacy and recruitment compliance | /hr/privacy/consent | Consent records are live, purpose/version/status controlled, and auditable. | Not Run
ROUTE-238 | Privacy and recruitment compliance | /hr/privacy/retention | Policies, triggers, periods, holds, owners, and reviews persist. | Not Run
ROUTE-239 | Privacy and recruitment compliance | /hr/privacy/deletion | Deletion requests verify identity/scope and respect hold/retention blocks. | Not Run
ROUTE-240 | Privacy and recruitment compliance | /hr/privacy/rtbf | RTBF assessment and permitted outcomes are documented and gated. | Not Run
ROUTE-241 | Privacy and recruitment compliance | /hr/privacy/audit | Immutable privacy events are live, searchable, and exportable by permission. | Not Run
ROUTE-242 | Privacy and recruitment compliance | /hr/privacy/recruitment-compliance | Live vacancy compliance records and compact row drawers work. | Not Run
ROUTE-243 | Privacy and recruitment compliance | /hr/privacy/employee-data-requests | Friendly create/detail surfaces and complete request lifecycle work. | Not Run
ROUTE-244 | Accounting integration routes | /accounting/coa | Payroll accounts can be created/edited and selected by payroll configuration. | Not Run
ROUTE-245 | Accounting integration routes | /accounting/journals | Payroll accrual/payment journals are balanced, linked, and not duplicated. | Not Run
ROUTE-246 | Accounting integration routes | /accounting/ledger | Posted payroll journal lines appear in correct accounts/period. | Not Run
ROUTE-247 | Accounting integration routes | /accounting/trial-balance | Payroll postings preserve balanced trial balance. | Not Run
ROUTE-248 | Accounting integration routes | /accounting/pnl | Salary/payroll expense appears in the correct period. | Not Run
ROUTE-249 | Accounting integration routes | /accounting/balance-sheet | Payroll/statutory liabilities and settlement balances are accurate. | Not Run
ROUTE-250 | Accounting integration routes | /accounting/cashflow | Posted salary payment appears in the correct cashflow classification. | Not Run

## Reconciliation
HR & Payroll Reconciliation
Financial and population controls required before production approval.
Reconciliation | Expected | Actual | Result | Evidence | Owner | Date | Comments
Current employee directory | Canonical current employee population |  | Not Run
Workforce headcount | Same as current employee population |  | Not Run
Compensation headcount | Same eligible population for period |  | Not Run
Payroll run item count | Eligible payable employees only |  | Not Run
Payroll gross | Sum of employee item gross |  | Not Run
Payroll deductions | Sum of employee deductions and tax |  | Not Run
Payroll net | Gross minus deductions |  | Not Run
Accrual journal | Debits equal credits |  | Not Run
Payment journal | Debits equal credits |  | Not Run
Published payslips | Finalized eligible payroll items |  | Not Run
Attendance posted rows | Valid nonduplicate matched rows |  | Not Run
Approved leave movement | Approved working days |  | Not Run
Separated employees in current selectors | 0 |  | Not Run

## Defect Log
HR & Payroll Defect Log
Record every failure and link it back to a stable test or route coverage ID.
Defect ID | Test / Coverage ID | Domain | Severity | Summary | Steps to Reproduce | Expected | Actual | Owner | Status | Raised Date | Target Date | Retest Result | Retest Evidence | Comments

## Test Data & Users
Test Data and Users
Use fictional, tenant-scoped data. Do not store passwords or production secrets in this workbook.
Type | Reference / User | Role / Purpose | Tenant | Status | Owner | Notes
User | HR-PREP | HR operations/recruiter |  | Not Prepared
User | MANAGER-A | Line/hiring manager |  | Not Prepared
User | HR-APPROVER | HR approver |  | Not Prepared
User | PAY-PREP | Payroll operator |  | Not Prepared
User | PAY-APPROVER | Payroll approver |  | Not Prepared
User | PAY-AUTH | Payment authorizer |  | Not Prepared
User | FINANCE | Accountant |  | Not Prepared
User | PRIVACY | Privacy/compliance |  | Not Prepared
User | EMPLOYEE-A | Employee self-service |  | Not Prepared
User | RESTRICTED | Read-only negative testing |  | Not Prepared
User | TENANT-B-ADMIN | Tenant isolation |  | Not Prepared
Data | E2E Operations <RUN> | Department |  | Not Prepared
Data | E2E Operations Analyst <RUN> | Position |  | Not Prepared
Data | E2E Candidate <RUN> | Candidate |  | Not Prepared
Data | CC-E2E-<RUN> | Cost centre |  | Not Prepared
Data | Future open period | Payroll period |  | Not Prepared

## Sign-Off
Production Readiness Sign-Off
Production remains not approved until every required owner approves and exit criteria are satisfied.
Approval Area | Name | Decision | Date | Signature / Reference | Conditions / Comments
Product Owner |  | Pending
HR Process Owner |  | Pending
Payroll / Finance Owner |  | Pending
QA Owner |  | Pending
Technical Owner |  | Pending
Security / Privacy Owner |  | Pending

## Lists (hidden)
Result | Severity | Defect Status | Preparation Status | Decision
Not Run | Critical | Open | Not Prepared | Pending
Pass | High | In Progress | Ready | Approved
Fail | Medium | Ready for Retest | In Use | Rejected
Blocked | Low | Closed | Retired
N/A |  | Deferred
Rejected